Business Case

Internship Placement Process Optimization

1. Business Background

TalentBridge Consulting is a mid-sized education and career advisory company that partners with universities and private organizations to facilitate internship placements for undergraduate and graduate students. The company acts as an intermediary between students seeking internships and organizations offering short-term professional opportunities.

Over the past two years, TalentBridge Consulting has experienced a significant increase in the number of student applicants, while its internal internship placement process has remained largely manual and fragmented. As a result, operational inefficiencies have begun to affect placement timelines, stakeholder satisfaction, and overall service quality.

2. Problem Statement

The current internship placement process is inefficient and lacks standardization. Key issues identified by management include:

- Delays in matching students with internship opportunities

- Inconsistent communication between students, employers, and internal staff

- Limited visibility into application status and placement progress

- High dependency on manual tracking using emails and spreadsheets

These challenges have led to extended placement cycles, increased administrative workload, and dissatisfaction among both students and partner organizations.

3. Business Impact

If the current process remains unchanged, TalentBridge Consulting risks:

- Reduced placement success rates

- Loss of partner organizations due to slow response times

- Lower student satisfaction and reputational damage

- Increased operational costs caused by repetitive manual tasks

Improving the internship placement process is therefore critical to maintaining service quality, operational efficiency, and competitive positioning in the education services market.

4. Project Objectives

The primary objectives of this project are to:

- Analyze the existing (AS-IS) internship placement process

- Identify process bottlenecks, inefficiencies, and gaps

- Design an improved (TO-BE) process that enhances efficiency and transparency

- Define clear business and functional requirements for a potential digital tracking solution

- Improve communication and coordination between all stakeholders

5. Project Scope

In Scope:

- End-to-end internship placement workflow analysis

- Stakeholder interaction mapping

- Process redesign and optimization

- Requirements documentation for process improvement

Out of Scope:

- Software development or system implementation

- Contract negotiation with partner organizations

- Legal or compliance restructuring

6. Success Criteria

The project will be considered successful if:

- Internship placement cycle time is reduced

- Process steps are clearly documented and standardized

- Stakeholders have improved visibility into placement status

- Administrative workload is reduced through clearer workflows

7. Assumptions and Constraints

Assumptions:

- Stakeholders are available for interviews and feedback

- Existing process documentation is limited

Constraints:

- No immediate budget for system development

- Process improvements must align with existing organizational structure