Stakeholder Analysis

Internship Placement Process Optimization

1. Purpose of Stakeholder Analysis

The purpose of this stakeholder analysis is to identify all key parties involved in the internship placement process, understand their interests and pain points, and assess their influence on the project outcome. This analysis will support effective communication, requirements gathering, and process redesign.

2. Stakeholder Identification

| Stakeholder | Role Description | Interest Level | Influence Level |
| --- | --- | --- | --- |
| Students | Apply for and participate in internships | High | Medium |
| Partner Organizations | Offer internship positions | High | High |
| Internship Coordinators | Manage placement workflow | High | High |
| Career Advisors | Support students during placement | Medium | Medium |
| Operations Manager | Oversees efficiency and performance | Medium | High |
| Executive Management | Strategic decision-making | Low | High |

3. Stakeholder Needs and Pain Points

Students

- Need timely feedback on application status

- Experience uncertainty due to lack of transparency

- Receive fragmented communication across channels

Partner Organizations

- Expect quick access to suitable candidates

- Experience delays in shortlisting and coordination

- Lack visibility into candidate readiness

Internship Coordinators

- Handle high volumes of applications manually

- Rely heavily on email and spreadsheets

- Experience workload peaks and process bottlenecks

Career Advisors

- Require up-to-date placement status

- Often receive incomplete information

- Have limited involvement in process decisions

Operations Manager

- Needs standardized workflows

- Lacks performance metrics (cycle time, success rate)

- Faces difficulty scaling operations

Executive Management

- Focused on placement success rates

- Concerned with stakeholder satisfaction

- Requires high-level reporting

4. Stakeholder Communication Strategy

| Stakeholder | Communication Type | Frequency |
| --- | --- | --- |
| Students | Status updates, notifications | Weekly |
| Partner Organizations | Candidate updates, confirmations | Per placement |
| Internship Coordinators | Internal coordination meetings | Daily |
| Career Advisors | Summary reports | Bi-weekly |
| Operations Manager | Performance dashboards | Monthly |
| Executive Management | Strategic summaries | Quarterly |